## Planning
PROJECT NAME:- Chat Bot | VMS
Document No/Name:-CHAT BOT 08/Project Planning phase | ame :Plan VMS
Project Planning Phase:-
Phase | Activity | Schedule |  | Time Line(days) | Deliverables | Resource Requirment
|  | Start date | End date |  |  | Hardware | Software | Human Resource
Planning | Project planning | 11/1/17 | 2017-01-15 | 5 | Plan documents. | Desktop with 64 bit | Android Studio and Eclipse. | Ambadas Madake
Designing | Project designing | 2017-01-16 | 2017-01-17 | 2 | Wire Frames | operating system and 4GB RAM. |  | Anuradha Wagh
Development | Creation of UI and Data Base . | 2017-01-18 | 2017-01-20 | 3 | UI screens and Database in mysql. |  |  | Vikas Lakade
Development | Data Storing.(Get ,Post )Request | 2017-01-21 | 2017-01-22 | 2 | input from UI and Data Store to database |  |  | Kshitij Suralkar
Development | Fetch data from database | 2017-01-23 | 2017-01-23 | 1 | Retrieve data as per query requirment.
Release | Project release | 2017-01-24 |  | 1 | Different release version control Actual deployment of project.